## Sheet1
TimeLine (1 sprint ~= 1 week or bi-week)
Tasks Checklist | Description | Responsible Roles | 1-2 Sprints | 2-4 Sprints | 4-6 Sprints | 6-8 Sprints | 8-10 Sprints
Business Clarification | Identify your business models, like system overview, system architect | Migration Architect Market Team Cloud Operations Manager
Identify dependencies and boundaries among different systems
Identify your business strategy objectives
Identify your business development plan
Evaluate new cloud-enabled revenue models
Staff Organization | Identify your user profolio, including internal employees, external customers | Migration Architect Human Resource Cloud Operations Manager
User Identity Access Management and SSO
Team Re-Organization (Leadership, Workforce, etc)
Cloud training and culture evolution
Platform Evolution | Identify your gaps between existing platform and cloud platform | Migration Architect Development Team Cloud Operations Manager
Identify existing technology stacks and its extension to cloud platforms
Re-architect the platform, infrastructure overview, middleware, applications
Provisioning and orchestration
Continous Integration and Continous Delivery
Data Migration | Identify data structure for different business models | Migration Architect Data Team Cloud Operations Manager
Research proper data storage, like Block storage, file storage, object storage
Identify data cost management based on different storage medium
Identify data redundancy or data backup for speeding access
Identify data insights, analytics, reporting
Security | Identify valnerabilities, system risks, and known cyber threats | Migration Architect Cloud Security Manager
Always ensure AuthN and AuthZ for data access, limit user access with Just-In-Time and Just-Enough-Access, and data protection
Define playbook for incident response
Prioritize data privacy and protection, plan risk management and data loss protection
Monitoring maclious activities, alerts, reporting and improve defences
Backup, Rollback and Disaster Recovery | Create a rollback plan for failure migrations or deployment and roll back to a good state | Migration Architect Cloud Operations Manager
Implement database versioning and prepare rollback procedures
Considering version control in critical assets or resources
Considering backup, replicas for desired and last-known-good configurations across different available zones or regions